Project Plan

Move-In

| Industry Partner |  |
| --- | --- |
| Primary Instructor | Laily Ajellu |
| Team Member | Lakshay Dhawan |
| Team Member | Ayesha Akbar |
| Team Member | Suthan Sureshkumar |
| Team Member | Sofia Beliak |
| Team Member | Arina Mirzakhani |

Document Revision History

| Revision # | Date |
| --- | --- |
| Version 3.0 | 06/02/2026 |

Table of Contents

1. Executive Summary

The following describes the project to be executed.

| Objective | Develop the Move-In website platform, a social moving marketplace that lets users book trucks and moving services online. Customers will benefit from clear pricing, approved reviews, and a safe payment system, while vendors and independent truck owners may advertise their services. Executive Summary - Minimum of 1 sentence improved or added - We have divided each role of which student will be working on - Started working on the G=it repo, on designing and the web UI, and as well as the database backend |
| --- | --- |
| Corporate Goals Addressed | - Improve moving services transparency and increase trust (addresses scams concerns and hidden costs) - Provide independent movers with access to a digital platform so they may connect with new clients - Make it easier for customers to make choices by providing search, filter and compare options - Encourage the growth of small businesses through fair competition |
| Planned Start Date |  |
| Planned End Date |  |

2. Project Approvers, Reviews and Distribution List

Approvers, reviewers and distribution list

| Project Role | Name | E-mail | Date |
| --- | --- | --- | --- |
| Design/documentation | Sofiia Beliak | Sofiia.beliak@georgebrown.ca | 06/02/2026 |
| Front-End Developer | Arina Mirzakhani | Arina.mirzakhani@georgebrown.ca | 06/02/2026 |
| Database Management | Suthan Sureshkumar | Suthan.sureshkumar@goergebrown.ca | 06/02/2026 |
| DevOps Engineer | Lakshay Dhawan | Lakshay.Dhawan@georgebrown.ca | 06/02/2026 |
| Back-End Developer | Ayesha Akbar | Ayesha.akbar@georgebrown.ca | 06/02/2026 |

3. Scope

Define the sum of all its products and their requirements or features.

| In Scope | Out of Scope |
| --- | --- |
| User account management – Implementing multiple user roles: Guest, Registered User, Vendor, Staff and Manager each with their own permissions | Public deployment – Hosting the site on a paid domain or cloud beyond the free tier and running live transactions with real payment data |
| Listings management – Allowing Vendors and Independent Vehicle Owners to create, edit, delete and publish listings with photos, pricing and availability | Marketing campaign – Creating a marketing plan and partnering with real vendors or customers to use the app |
| Search and filtering functionally – User can browse using filter such as location, price, vehicle size, service type and more | Regulatory and legal compliance – Handling actual insurance verification, license checks, or background screenings. Aswell as managing tax reporting, business registration, or any service liability coverage. |
| Booking and reservation system – User can view real-time availability and can make bookings and receive confirmations | Mobile application development – Developing separate builds for Android/iOS and creating a downloadable version in their respective app stores |
| Rating and review system – Adding a two-way feedback system which allows both customers and vendors to rate each other after service | Full financial processing – Integrating a full accounting, payout and real bank transfer system to vendors. Also implementing a full refund, dispute or escrow system. |
| Notification system and communication system – Implementing email, SMS and in app notifications for booking, updates and cancellations | Advanced machine learning or AI features – Creating a recommendation system (e.g. “this is the best mover for you”) and any predictive analysis |
| System documentation and testing – Providing UML diagrams, ERD, test reports and project documentation | Cloud scalability automation – Using Kubernetes or load balancers for large scale traffic |
| Authentication and authorization – Securely registering users and encrypting sensitive information | Multi-country expansion – Supporting internation currencies, languages or legal frameworks |
| Database design and implementation – Structured relational database to manage users, listings bookings and reviews | Offline mode support-Using the application without internet access |
| Admin/Manager dashboard – Creating a dashboard for staff or managers to manage listings, view reports and handle disputes | Real-time GPS tracking- Live tracking of vehicles or vendors during service execution. |
| Version control – Using GitHub for code versioning and team collaboration | Customer support call center- 24/7 live phone or human chat support |

4. Deliverables

This project will deliver the following.

| Deliverable | Description |
| --- | --- |
| Project Documentation | Vision, high-level requirements, system summary, architecture documentation, API specifications, UI design system, and ongoing documentation updates during implementation. |
| Database Design and Implementation | ERD, schema creation, database setup, and integration with backend services to support application functionality. |
| UI/UX Design | Responsive and user friendly front-end for each user role, including implemented UI components and role-based dashboards. |
| Functional web application | Web application which supports listing creation, booking and payments, with core features actively implemented and integrated across frontend and backend. |
| Booking system | Real-time availability and reservation system with backend logic, API endpoints, and frontend interactions. |
| Review and Rating System | Two-way review system for customers and vendors, designed and prepared for integration into the application workflow. |
| Testing Report | Unit and integration testing of implemented features to ensure system reliability and correctness. |
| Presentation | Final demonstration and project presentation showcasing implemented features and project outcomes. |

5. Assumptions

This project makes the following assumptions;

- There will be potential market demand for people who wants to rent or list moving vehicles and services.

- Truck owners will follow local laws and keep their insurance active.

- Users will share honest and fair reviews.

- Users will feel safe and confident using online payment system.

- Third-party APIs will be functional and available throughout the development

- Vendors and owners will provide accurate information and photos about their vehicles and services.

- All the users will have a stable internet connection and a device to use the web app.

- Team members will contribute consistency and meet project deadlines

- The development and test environment will be available and operation throughout until competition

- The project has been initiated,and the team has begun the planning and development phases.

6. Dependencies

The following are the internal and external dependencies that will have to be acknowledged and addressed;

- The payment system used for processing payments. Our payment processing is dependent on third party payment processing company like Stripe.

- As a team we our dependant on tools such as GitHub, Discord, and Microsoft Office for team collaboration, communication and version control.

- We will be using a service like Twilio communication and notifications within the application, by Vendors/ truck owners, users and staff.

- The success of our software is dependent on the truck owners and moving vendors that would be listing their services on our platform. This would ensure that the users that visit the platform are able to book the services they require.

- Mapping feature used in the application is reliant on services like Google Maps to provide location details etc.

- The scope of the project is limited to the current knowledge and skills of the members.

- Successful completion of our project requires all members have functioning computers, IDEs, and internet access

- The timeline for the project completion is limited to the end of the winter 2026 semester, which is a total of 8 months as well as the availability of team members availability.

- Our back-end operations depend on the correct setup and configuration of the project’s database

- Insurance coverages need to be secured prior to services begin so there are no liability issues when a renter operates someone’s vehicle on the platform. We also need to confirm that the vendors and truck owners have their own insurance to make sure the customers are covered in case there is any damage to their belongings when moving.

7. Risk Management

| Potential Risk | Severity (H/M/L) | Likelihood (H/M/L) | Management Strategy |
| --- | --- | --- | --- |
| Cybersecurity breach or data leak | High | Low | Use secure coding practices such as input validation and HTTPS in deployment |
| Low vendor acceptance rate | Medium | High | Support initial movers and offer clear training |
| Hidden costs | High | Medium | Clear price breakdown in the system |
| Delay in feature development and integration | High | Medium | Have internal deadlines and have weekly meetings to track progress. Also assign other members to help in completion |
| API integration issues | High | Medium | Have an alternative API option |
| Version control conflicts | Medium | High | Use a branched based Git workflow and do regular merges |
| Limited technical expertise | Medium | Medium | Self-learn and use official documentation and tutorial for guidance |
| Inconsistent team communication | Medium | Medium | Have mandatory weekly meetings and use a shared online chat |
| Hardware failure | Medium | Low | Use GitHub for version control and push any changed daily to avoid data loss |
| Team member illness or unavailability | Medium | Low | Redistribute task temporarily and track changes for transferring tasks |
| Documentation errors or missing sections | Low | Low | Assign a documentation lead to review and standardize all deliverables |
| Version control conflicts during parallel development | Medium | Medium | Use a feature-based branching strategy, regular pulls, pull requests, and code reviews before merging changes into the main branch. |

8. Communication

Reporting

The following reports will be produced;

| Report | Audience | Frequency |
| --- | --- | --- |
| Project Summary | Team Members | At the start of the project and updated as needed |
| Project Vision Document | Stakeholders, Development team | Submitted at project initiation and updated as needed |
| High Level Requirements Document | Stakeholders, Development team | Once finalized during sprint 1 and reviewed again at the beginning sprint 2 |
| Document Approval List | Instructor | Updated whenever a document is approved |
| Document Distribution List | All project team members | Updated whenever a new version of any project document is released |
| Attachments and Referenced Documents | All project team members | As needed attached to each submission or update |

Meetings

The following meetings/communication will be established;

| Meeting | Purpose | Attendees | Frequency |
| --- | --- | --- | --- |
| Sprint planning | Generate ideas, work on files | Whole team | 2 times a week |
| Check-ins | Check work progress, add/edit things | Whole team | 3 times a week |
| Sprint review | Review and submit | Whole team | End of sprint |

9. Task Listing (WBS- Work Breakdown Structure)

The following resource proposal template summarizes the resource hours committed to this project, upon final approval of this document.

| Ref | Task | Duration | Dependency |
| --- | --- | --- | --- |
| A | Project Documentation | 4 weeks | N/A |
| A1 | Project Initiation & Planning | 3 days | N/A |
| A2 | Project Summary & Vision | 3 days | A1 |
| A3 | High-Level Requirements | 3 days | A2 |
| A4 | Personas & User Stories | 3 days | A3 |
| A5 | Project Plan | 5 days | A4 |
| A6 | Team Charter | 2 days | A5 |
| A7 | Product & Sprint Backlog | 3 days | A6 |
| A8 | Requirements, Analysis & Design Document | 5 days | A7 |
| A9 | Create wireframes and prototype UI screens for all user roles | 4 days | A8 |
| A10 | Technology Requirements | 3 days | A9 |
| A11 | Final Documentation Compilation – Review and combine all documents into final package | 4 days | A10 |
| B. | Database Design & Implementation | 3 weeks | A |
| B1 | Design ERD and define relational data models | 1 week | A |
| B2 | Create and configure database schema | 1 week | B1 |
| B3 | Integrate database with backend services | 1 week | B2 |
| B4 | Test data storage and queries for listings, bookings, and reviews | 3 days | B3 |
| C. | UI/UX Design | 3 weeks | A |
| C1 | Create detailed UI wireframes for user roles (guest, vendor, staff, admin) | 1 week | A |
| C2 | Build responsive front-end structure | 1 week | C1 |
| C3 | Implement visual enhancements | 1 week | C2 |
| C4 | Conduct UI usability testing and gather feedback | 3 days | C3 |
| D. | Functional Web Application | 6 weeks | B, C |
| D1 | Implement user authentication, registration, and role-based access | 1 week | B, C |
| D2 | Develop vehicle and service listing CRUD features | 1.5 weeks | D1 |
| D3 | Create user dashboard and profile management | 1 week | D2 |
| D4 | Integrate frontend with backend APIs | 1.5 weeks | D2 |
| D5 | Optimize application performance and error handling | 1 week | D4 |
| E. | Booking System | 3 weeks | D |
| E1 | Develop real-time booking and scheduling logic | 1 week | D |
| E2 | Integrate booking flow with payment and notifications | 1 week | E1 |
| E3 | Implement booking confirmation pages and cancellation flow | 1 week | E2 |
| F. | Review & Rating System | 2 weeks | D |
| F1 | Develop review submission and display functionality | 1 week | D |
| F2 | Enable two-way feedback between customers and vendors | 1 week | F1 |
| F3 | Add review moderation and reporting features | 3 days | F2 |
| G. | Testing & QA Report | 2 weeks | D, E, F |
| G1 | Write unit and integration tests | 1 week | D, E |
| G2 | Perform full system testing and resolve defects | 1 week | G1 |
| G3 | Document all testing results in a formal QA report | 3 days | G2 |
| H. | Presentation & Delivery | 1 week | G |
| H1 | Prepare project presentation slides and demo environment | 3 days | G |
| H2 | Conduct mock demos and internal reviews | 1 week | H1 |
| H3 | Finalize and deliver presentation to instructor | 3 days | H2 |

10. Gantt Chart

Create a detailed Gantt Chart from your Task Listing(Use any software tool and paste the image or upload as a separate file that can be opened as pdf/doc/xls)

11. Milestones

| Major Activity or Milestone | Estimated Milestone Target date | Owner/Reviewer Team Members |
| --- | --- | --- |
| Completion of Project Documentation (A1–A11) | Week 4 | Front-End Developer |
| Database Design & Integration Completed (B1–B4) | Week 7 | Back-End Developer |
| UI/UX Design Finalized (C1–C4) | Week 10 | UI/UX Designer |
| Core Functional Web Application Developed (D1–D5) | Week 14 | Full Stack Team |
| Booking & Review Systems Implemented (E1–F3) | Week 16 | Back-End Developer |
| QA Testing Completed & Report Submitted (G1–G3) | Week17 | Project Manager |
| Final Presentation & Delivery (H1–H3) | Week 18 | All Team Members |

12. RAM – Responsibility Assignment Matrix

Create a RAM from your Task Listing. A sample is shown below:

| Major Task / Phase | Arina (Front-End) | Ayesha (Back-End) | Suthan (Database) | Sofiia (Design/Docs) | Lakshay (DevOps) |
| --- | --- | --- | --- | --- | --- |
| A. Project Documentation Completed | S | S |  | P | S |
| B. Database Design & Implementation |  | S | P | S | S |
| C. UI/UX Design Finalized | S |  |  | P |  |
| D. Core Functional Web Application Development | P | P | S | S | S |
| E & F. Booking & Review Systems Implementation | S | P | S | S |  |
| G. Testing & QA Report Completed | S | S |  |  | P |
| H. Final Presentation & Delivery | P |  |  | P | S |

13. Approval

The signatures below indicate their approval of the contents of this document.

| Project Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Design/documentation | Sofiia Beliak | Beliak | 06/02/2026 |
| Front-End Developer | Arina Mirzakhani | 𝒜𝓇𝒾𝓃𝒶𝑀𝒾𝓇𝓏𝒶𝓀𝒽𝒶𝓃𝒾 | 06/02/2026 |
| Database Management | Suthan Sureshkumar | Suthan Sureshkumar | 06/02/2026 |
| Back-End Developer | Ayesha Akbar | ayesha | 06/02/2026 |
| DevOps Engineer | Lakshay Dhawan |  | 06/02/2026 |